## Sheet1
# | Task | Week 1 (31 Mar) | Week 2 (7 Apr) | Week 3 (14 Apr) | Week 4 (28 Apr) | Week 5 (2 May)
1 | User needs assessment | XXXXX
1.2 | Feature prioritization | XXXXX
1.3 | System constraints definition | XXXXX
1.4 | Use case development | XXXXX
1.5 | Inventory tracking requirements | XXXXX
1.6 | Data storage requirements | XXXXX
1.7 | User interface requirements | XXXXX
1.8 | Performance requirements | XXXXX
2 | Class hierarchy planning | XX | XXX
2.2 | Database schema design | XX | XXX
2.3 | UI wireframing |  | XXXXX
2.4 | Algorithm design for storage optimization |  | XXXXX
2.5 | Error handling strategy |  | XXXXX
2.6 | Design patterns selection |  | XXXXX
3 | Product class implementation |  | XXXXX
3.2 | Location class implementation |  | XXXXX
3.3 | Warehouse class implementation |  | XX | XXX
3.4 | Class relationship implementation |  |  | XXXXX
3.5 | Validation logic development |  |  | XXXXX
3.6 | Exception handling implementation |  |  | XXXXX
3.7 | Product-location association logic |  |  | XXXXX
4 | 2D grid representation |  |  | XXXXX
4.2 | Status indicators for locations |  |  | XXXXX
4.3 | Dynamic updates |  |  | XXXXX
4.4 | Color coding implementation |  |  | XXXXX
4.5 | Location capacity visualization |  |  | XXXXX
4.6 | Warehouse statistics display |  |  | XXXXX
4.7 | Grid navigation controls |  |  |  | XXXXX
4.8 | Data visualization patterns |  |  |  | XXXXX
5 | Product management interface |  |  | XX | XXX
5.2 | Location management interface |  |  | XX | XXX
5.3 | Search functionality |  |  |  | XXXXX
5.4 | Reporting capabilities |  |  |  | XXXXX
5.5 | CSV import/export |  |  |  | XXXXX
5.6 | Batch operations processing |  |  |  | XXXXX
5.7 | Low stock notifications |  |  |  | XXXXX
5.8 | User activity logging |  |  |  | XXXXX
6 | Unit testing |  |  |  | XX | XXX
6.2 | Integration testing |  |  |  | XX | XXX
6.3 | Error handling validation |  |  |  | XX | XXX
6.4 | Performance optimization |  |  |  |  | XXXXX
6.5 | Edge case testing |  |  |  |  | XXXXX
6.6 | Stress testing warehouse capacity |  |  |  |  | XXXXX
6.7 | User input validation testing |  |  |  |  | XXXXX
6.8 | Cross-platform compatibility |  |  |  |  | XXXXX
7 | User acceptance testing |  |  |  |  | XXXXX
7.2 | Documentation finalization |  |  |  |  | XXXXX
7.3 | Code review and refactoring |  |  |  |  | XXXXX